## Sheet1
Development Schedule
Task | Expected Completion Date | Completed | Description
Relational Model
Create Relations in MySQL database | 2026-04-12 | Done | Generate the schema for the SQL Database
Generate Testing Data (Populate Relations) |  | Done
Create code to generate Testing data | 2026-04-14 | Done | Create Sample data that can be imported into the database
Create Queries |  | Done
Sales Trends by Year, Month, Week -> Gender + Income | 2026-04-17 | Done | Generate the SQL queries
Identify what cars contain parts by supplier made between dates. Locate VIN and customer
Top 2 brands by sale price
Top 2 brands by units sold
Best months for convertibles
Dealerships that keep inventory for the longest average time
Generate Interfaces |  | Done |  | _
Generate UI | 2026-04-18 | Done | Generate a simple button UI for each of these portals
Customer
Sales
Main Menu
Customer Portal
Marketing Portal
Vehicle locator |  | Done
Local and nearby implementation | 2026-04-20 | Done | Create the Vehical locator which has distance and option matching
Options matching
Integrate Concurrency | 2026-04-25 | Done
Java Implementation | 2026-04-22 | Done
Testing | 2026-04-26 | Done
Update ER Diagram | 2026-04-23 | Done
Create README File | 2026-04-28 | Done
Submit Files | 2026-04-30